## Sheet1
Product backlog
Planning
Building
Task | sub task | Difficulty | Time (minutes)
Frame and section spacing |  | 1 | 20
Outline | Banner and nav | 1 | 15
| image | 1 | 15
| about | 2 | 20
| services | 2 | 20
| contact | 3 | 40
| footer | 1 | 10 | 140
Responsive design | banner and nav | 2 | 30
| image | 2 | 30
| about | 2 | 30
| services | 2 | 30
| contact | 2 | 30
| footer | 1 | 15 | 165
Visual Design | banner and nav | 2 | 30
| image | 2 | 20
| about | 2 | 30
| services | 2 | 30
| contact | 2 | 30
| footer | 1 | 15 | 155